## Project_Schedule
| Phase of Development | Activities to be carried out | Deadline
1 | Analysis and Specification | For the development of the project, I analysed the currently available systems. I tried to solve the accuracy issues in those system. And for solving the accuracy issues I used the texture based facial recognition algorithms which do not depend upon facial features instead uses texture for the task. After all the analysis, for adding the other features such as live streaming and mark and view the attendance through the website. I used the flask framework which is different from other available systems.
2 | Designing | For designing purpose, we used Python language as our the main language for scripting in our project. The libraries used for designing of the overall code were OpenCV, Paddlehub and the framework used is the FLASK framework. And various different tools used for designing the code were Anaconda, Spyder,XAMPP and Visual Studio.
3 | Implementation | For Implementation, we implemented the following : 1. Face and Mask Detection using Paddlehub's Pyramidbox server mask model 2. Face Recognition using LBPH 3. Attendace Functionality 4. Live Streaming Functionality in Webpages 5. Web development (Dashboard and login) 6. Graph and Trends Via Chart.JS 7. Admin and Student Profiles
4 | Testing | This was the final phase of our project in which we tested the project on different aspects. One aspect of testing of our project was the accuracy of our model. The next aspect of testing was creation of the statistics graph creates. And the final testing was performed on the overall working of the project.

## Record of Activities(Monthwise)
Month | 2020-10-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This was the ideation phase for our project where we researched and discussed what technology should the team use to perform masked facial recognition.
Week2 | We decided to use the time to collect some dataset which would be useful in the future weeks and concentrated on using the upper half of the face to perform facial recognition. We collected two sets of dataset one of standard resolution and other HD resolution
Week3 | This week we tested various facial recognition technologies like facenet, LBPH, etc. We trained and tested them with the dataset collected periously.
Week4 | We researched and tested some of them and decided to use the LBPH algorithm as it gave good results. And continued to get higher quality dataset of the team members and their family for future use and testing.
Month | 2020-11-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | We implemented the LBPH facial recognition Algorithm such that it could process input from a video or a live camera feed. Demo video of this implementation was submitted to our mentor.
Week2 | During testing of facial recognition, we noticed that “Haarcascade Frontal Face” a face detection algorithm, was not giving consistent results as it was not developed with masked faces in mind.
Week3 | This week we were tasked to create and deploy a simple static web page through AWS which was done using an EC2 instance. At the same time we were researching various mask detection techniques.
Week4 | This week concentrated on working on the issue of Masked-face detection which came up in Week 2 of the month. we decided to use the PyramidBox-Lite Mask Detection model developed by baidu. This model was able to fix the previous issue.
Month | 2020-12-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week we implemented mask detection such that it could process input from a video or a live camera feed and the demo video of this implementation was submitted to our mentor.
Week2 | This week we concentrated on integrating the previously built parts of the project i.e Masked face detection, mask detection and masked face recognition, into a single script.
Week3 | This week we concentrated on bug fixing and testing of the project after the integration. The demo video of this implementation was submitted to our mentor.
Week4 | This week we worked on the update functionality of the project which enabled us to add new faces into the model, so that we don’t have to make a whole new model everytime we add a new face into the model.
Month | 2021-01-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week we created a demo video showcasing all the features and progress of the project along with the project report as part of Minor submissions
Week2 | Project on hold due to 7th Semester Final Examinations
Week3 | Project on hold due to 7th Semester Final Examinations
Week4 | This week worked on the Live Stream functionality using Flask framework which enabled us to host our model in the form of a website, which could be used to mark the attendance with a camera.
Month | 2021-02-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week worked on the MySQL database which involved the database design, table design, giving the tables respective constraints and relationships so that it would work seamlessly with the rest of the code.
Week2 | This week we worked on the attendance functionality which is used to mark the attendance into the database, where we created relevant SQL commands which were compatible with the constraints created in the previous week in the database.
Week3 | We integrated the attendance functionality with previously developed code to work in tandem with the model. after brief testing. The demo video of this implementation was submitted to our mentor.
Week4 | This week we tested our previous implementation to iron out the bugs. The demo video of this implementation was submitted to our mentor.
Month | 2021-03-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week we streamlined our code by converting almost every action taken by the program from multiple files to smaller functions and removed the redundant code.
Week2 | This week after streamlining the script, we changed parts of it so that we could perform mask detection and mask-face recognition of multiple users at the same time, if they are in the frame.
Week3 | We tested these new features this week and integrated it with the main project. The demo video of this implementation was submitted to our mentor.
Week4 | This we finalized on the UI design and the front-end design. We concluded it would best to go with minimalist design using bootstrap as our front-end frame work.
Month | 2021-04-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week we integrated all our previous work with the live stream functionality and tested it briefly and fixed the bugs which cropped up during the integration.
Week2 | This week we created a presentation to showcase our progress, explaing the tecnologies used and a demo video of the same was also created and was submitted to our mentors.
Week3 | This week we created features to the dashboard which included tables using bootstrap, graphs using chartjs and trends from the data in the database.
Week4 | This week we added the “Exit cam” to record the Exit times for the user, adjusted the database (i.e. created a separate table to hold the exit timing) accordingly and created a table to showcase Entry and Exit times together.
Month | 2021-05-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week we added the Add User functionality and created the user page so that a registered user can view his or her attendance after logging in into the system (i.e. his or her profile).
Week2 | We integrated the previously made features with the main code. Streamlined the whole script and updated it into our github. Proceeded to work on the documentation.
Week3 | This week we added the readme.md portion of our github repository which included hardware requirements, setup guide, etc and submitted the deliverables
Week4 | This week, we finalized the project and made a video demo explaining the features of the project along with the project report for the final submision.